draft

Roadmap to AFA 2016 strategic plan

| 2014 | 2015 |  | 2016 |  | Remarks |
| --- | --- | --- | --- | --- | --- |
| Jul-Dec | Jan-Jun | Jul-Dec | Jan-June | Jul-Dec |  |
| EXTERNAL EVENTS |  |  |  |  |  |
|  | International Year of Soils |  | FAO Asia Pacific Regional Conference in Malaysia |  |  |
|  | FAO Symposium on Agro Ecology (tbc) | New Sustainable Devt Goals (SDGs) agreed upon at UN (Sept) | Global Farmers Forum (Feb) |  |  |
| AFA EVENTS |  |  |  |  |  |
| Review of Existing AFA Systems | A. national levels : review of strategic plan B. sub regional consultations : Review of Country /sub region Situationer, FO Growth Monitoring Tool; devt of sub regional agenda | AFA Execom : Strategic Planning Workshop ( a small group to be created to plan the process of the strategic planning exercise) | A. Drafting Milestones and Indicators of Plan ( in virtual work groups) | Resource Mobilization for the Plan |  |
|  |  |  | B. AFA General Assembly ; -approval of Strategic Plan and MIlestones/ operations plan -Innovation Fair C. Donor’s Forum | Implementation of Plan |  |
| youth wing and youth development pogram | women’s wing and women’s development program in afa |  |  |  |  |
| MTCP2 SIS and RSC | input above in MTCP2 sub regional steering Committee meeting | input above in MTCP2 SIS and regional steering comm. meeting |  |  |  |