Annex 3:

AFA, Inc

Matrix on Projects

As of July 2015

(Used in last Execom. New updates in yellow.)

| Project Name | BUDGET (in USD) Total Approved Counter part |  |  | Funding Source | Timeframe | Aims | Main Activities | Covered Countries | Reporting Dates |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AGRITERRA: Advocacy for Gov’t. support to Sustainable Agr’l and Farmer Led Enterprises EXTENSION Jan-June, 2015 | 473,156 | 300,286 | 172,870 | AGRITERRA | Jan-Dec 2014 | -To influence nat’l, key inter-gov’t reg’l and int’l decision-making bodies to enact policies that will recognize family farming and that will support sustainable, family farming agri and improve the conditions and livelihoods of small scale women and men farmers. | -Nat’l Implementation of AFA FACT on Youth workplan -WS on Young Farmers agenda of AFA -2nd FACT WS Learning WS Parallel Sessions -FACT Trainers’ Training & Planning WS -Sharing session on FACT Youth -IYFF Posters & Issue papers -member to member cooperation -visit to members -research on Youth in Agri -issue paper on youth in agriculture -participation in international conferences | Philippines, Indonesia Thailand, Cambodia, Vietnam, Myanmar, Bangladesh, Nepal, South Korea, Japan, Taiwan, Mongolia, Kyrgyztan | -May, 2014 -February 1, 2015 STATUS: WITH EXTENSION UNTIL JUNE 2015; final report due July 31, 2015 |
| MTCP2: Medium Term Cooperation Programme with Farmers’ Organizations in Asia and the Pacific Region – Phase II | 4,917,200 | 4,917,200 |  | MTCP2- IFAD, SDC | Sept. 4, 2013 – Sept. 30, 2018 | -To strengthen the FOs in the Project Area in their capacities of engaging active policy consultants related to the rural smallholders’ interests at nat’l, sub-reg’l .& reg’l. levels -to provide improved and inclusive services to the rural poor. | -Strengthening of FOs and their Networks -Participation of FOs in Policy Process -FOs’ Services and Involvement in Agri Dev’t Programmes -Programme Mgt and Coordination | Philippines,Indonesia,Cambodia,Myanmar,Laos,Vietnam,China, Nepal, Sri Lanka, India, Bangladesh, , Fiji, Samoa, Tonga, Vanuatu, Solomon Islands . expansion to : Thailand, Bhutan, Pakisatan, Afghanistan | July and January of every year |
| CSA-PP ( Public Procurement): Expanding involvement of Farmers’ Organizations in Public Programs Generating Employment and Promoting Sustainable Agriculture | 48,840 | 26,040 | 22,800 | CSA | July 2014 – June 2015 | -Facilitate the dialogue between FOs and gov’t at various levels in order to promote public food purchase programs and to ensure the FOs involvement in those programs | -Knowledge Product Dev’t:case & video documentation -Reg’l Learning Session -Technical Assistance:link FO country anchors to relevant institutions -Project Monitoring & Evaluation | connected to Pakisama project with CSA - with regional learning session | June 30, 2015 STATUS: Extension until October 2015; final report on Nov 30, 2015 |
| CSA 5 Years Developing capacity of farmers’ organization on sustainable agro-enterprise through knowledge sharing and innovation |  | 36,400 |  | CSA | Oct 1, 2014 – Sept 30, 2015 | -improve the capacities of AFA national FO members to provide services to its members/farmers association particularly in managing sustainable agro-enterprises though knowledge sharing and innovation and capturing of lessons learned through guidelines frameworks, manual. | - Mapping/Scoping study and brief profile of various country models - National learning workshop - Documentation of the national learning sessions - | Philippines, Indonesia, Vietnam, Cambodia, Thailand, Myanmar, Laos | -Jan 31-Oct 30, 2015 |
| WRF-IYFF-IFAD Promoting Improved Policies in favour of Family Farming in Developing Countries | 75,850 | 22,000 | 53,850 | WRF-IFAD | Sept. 1, 2013 – Dec. 31, 2014 | -to improve national policies in favour of Family Farming, in the context of the IYFF-2014 in targeted regions and countries | initiating engagement with SAARC through SAARC seed bank | Nepal, Bangladesh | -Feb 2014 -July 2014 -April 2015 STATUS: CLOSED SATISFACTORILY |
| ILC VGGT Popularizing the VGGT among small-scale farmers’ organization, relevant national gov’t and inter-gov’t agencies | 97,400 | 70,000 | $27,400 | ILC-VGGT | Sept. 1, 2014 – Sept. 1, 2015 | -Deeper the understanding and appreciation of VGGT by farmer leaders and key gov’t officials at nat’l level amidst their current conditions and struggles on land issues | -Preparation of policy researches/paper -Conduct of National forum -Regional Learning Session -Finalization of papers | Bangladesh, Cambodia, Kyrgyzstan | October 1, 2015 |
| ILC-LM Land Matrix Development in Asia and the Pacific | 171,400 | 40,000 | 131,400 | ILC-LM | Aug 1, 2014 – Aug 1, 2015 | -give necessary data as well as necessary skills to get data -strengthen our partnership with other CSOs who are working on land rights issues as well | -Data collection -Netwrok Building/Strengthen -Research | Philippines,Indonesia,Cambodia,Vietnam, Thailand,Laos, Myanmar, Nepal, Bangladesh,India, Sri-Lanka, Pakistan | August 30, 2015 STATUS: EXTENSION TILL DECEMBER 30, 2015, final report due Jan 30, 2015 |
| FFF (Forest and Farm Facility) Strengthening Engagement of Asian small scale women and men forests and farm producers in global and regional processes |  | 100,000 |  | Forest and Farm Facility thru FAO | January-December 2015 | To consolidate the voices of members in 8 countries who are living in forested landscapes and thereby strengthen AFA’s legitimacy, accountability, representation and advocacy work with national, regional and global institutions deciding over forest and farm landscape matters as they relate to food security and nutrition, sustainable livelihoods, climate change, and poverty reduction concerns. | Local Consultations National Consultations (8 countries) Regional Sharing Session Research Report on the consultations Issue paper | Nepal, Myanmar,Vietnam Indonesia, Phils, Cambodia, Thailand, Vietnam, Myanmar, Nepal, Bangladesh | Aug 15, 2015; January 30, 2015 |
| GFAR FORESIGHT Catalytic Actions Contributing Towards Agricultural Research and Innovation for Development Outcomes as defined in the GFAR Medium Term Development Plan 2014-2017 | 53,000 | 53,000 | 0 | GFAR (global forum on agriculture research) through FAO | January-September 2015 | -support to grassroot organizations in implementing foresight based plans of action at local level -consolidated outputs from grassroot organizations to global debates on the future of food, agriculture and rural development | -regional traning workshop on grassroot foresight -3 local grassroot foresight workshop -research paper on implementation and lessons learned | -Indonesia Philippines -India | February 2015; October 2015 |
| PROJECTS IN PIPELINE (submitted but still under negotiations or already approved in principle but still waiting for contract) |  |  |  |  |  |  |  |  |  |
| GAFSP (Global Agriculture and Food Security Program) Support Organization for South Civil Society Organizations Under the Global Agriculture and Food Security Program | 85,000 | 85,000 | none | GAFSP | January-June 2015 | -to provide technical, administrative and logistical support to their respective CSO representative of the GAFSP steering committee -consultation among constituency CSO’s -dissemination of information to constituency CSO’s -dialogue between the CSO representatives and other members of the Streering Committee -dialogue between CSOs and Supervising Entities and governments at the national level | -making travel arrangement for the representative’s travel including to constituency countries for consultation and outreach and to Washington DC to attend GAFSP steering committee meeting - contracting services (e.g.resource persons, translators, workshop facilitators) or goods (e.g. office supplies) as needed - organizing meetings (in person, audio and video conference) and consultation workshops | CSO country missions in Laos Nepal Bangladesh Cambodia Mongolia Tajikistan Kyrgyztan Bhutan T Leste | approved by the GAFSP Steering Committee; waiting for contract |
| MTCP2 –ASEAN in AFOSP | 16,000,000 dollars | 7,700,000 dollars to AFA; 7,000,000 to Agricord 300,000 to IFAD mgt. | 1,000,000 | European Union ( EU) | July 2015-June 2020 60 months from June 2015 | - AFOSP is a capacity building programme aiming at improving the livelihoods and food security situation of smallholder farmers and rural producers in ASEAN countries. The AFOSP programme purpose is that ASEAN FOs evolve into stable, performing, accountable organisations capable of providing effective and sustainable services to their members and of influencing policy and corporate processes on agriculture and food security issues at local, national, ASEAN regional and global levels. Specific objectives : a. Strengthen FOs Institutional and Operational capacities b. Enable FOs at different levels to influence regional, national and provincial policies on smallholder priority subjects c. Improve FOs services to their members (entrepreneurial capacities and participation in value chains) AFOSP has two components : a. FFP/ASEAN – to be managed byAgricord b. MTCP ASEAN- to be managed by AFA | Component 1: Institutional strengthening of FOs and their networks Component 2: FO Participation in Policy Processes at national, sub regional and regional processes Component 3: FO Services and Involvement in Agriculture Development Programs Component 4: Support to ASEAN Foundation with cross cutting concerns on women, youth, good governance, environmental sustainability, disaster managment and reduction and climate change | ASEAN countries for MTCP2 ASEAN : activities at the continental, regional and national levels and to create institutional linkages between these platforms and ASEAN secretariat FFP/ASEAN : mainly involves local FOs and value -chains specialised FOs from the local to the national level. In fact, one of the main pillars of the FFP is the funding of small organisations and local associations. Such funding is directly contracted with the local organizations (not via national organizations). |  |
| FINISHED PROJECTS |  |  |  |  |  |  |  |  |  |
| GAFSP (Global Agriculture and Food Security Program) Support Organization for South Civil Society Organizations Under the Global Agriculture and Food Security Program |  | 42,498 |  | GAFSP | April 1, 2014- June 30, 2014 | -to provide technical, administrative and logistical support to their respective CSO representative of the GAFSP steering committee -consultation among constituency CSO’s -dissemination of information to constituency CSO’s -dialogue between the CSO representatives and other members of the Streering Committee -dialogue between CSOs and Supervising Entities and governments at the national level | -making travel arrangement for the representative’s travel including to constituency countries for consultation and outreach and to Washington DC to attend GAFSP steering committee meeting - contracting services (e.g.resource persons, translators, workshop facilitators) or goods (e.g. office supplies) as needed - organizing meetings (in person, audio and video conference) and consultation workshops | Nepal, Bangladesh | FINISHED. -May 15, 2014 -July 31, 2014 |
| ILC-GEC Building Farmers’ Capacities in Applying the GEC in Land through FO to FO Cooperation | 35,000 | 10,000 | 25,000 | ILC-KPA | December 2013 – May 2014 | -to increase awareness of AFA member Farmer Organizations on the gender evaluation criteria (GEC) -to apply the GEC criteria in analyzing the priority land issues of farmer organizations | -attendance to the Gender Evaluation Criteria Training -Formation of an Evaluation Team to Myanmar -Data gathering in Myanmar -Validation process | Myanmar, Philippines, Nepal | FINISHED: May 31, 2014 |
| ILC-PPP: Research on PPP model of the New Vision for Agricluture,Using a Gender Lens | 55,250.00 | 20,176 | 35,074 | ILC-KGA | August 2013 – April 30, 2014 | -Draw lessons and insights from current PPP model of the New vision for Agriculture, which will serve as inputs to various advocacy engagements on RAI. | -Prepare Case Study Methodology and outline -Data gathering -Analysis of Findings -Presentation of Findings and Analysis/Lessons | Vietnam, | FINISHED : July 30, 2014 |