AFA Plans

(July-December 2015)

32nd AFA Execom Meeting

DETAILS

(For reference. Translate if you want the full details.)

| SUMMARY OF AFA SECRETARIAT PLANS JULY-DECEMBER 2015 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | PIC | Jul | Aug | SEPT | OCT | NOV | DEC | 2016 |
| REGIONAL EVENTS |  |  |  |  |  |  |  |  |
| MTCP2 PHILFAFO small grp mission | LR | X |  |  |  |  |  |  |
| MTCP2 SRSC SA | LR | X |  |  |  |  |  |  |
| MTCP2 SRSC SEA | LR |  |  | X |  |  |  |  |
| MTCP2 RSC | LR |  |  |  |  | X |  |  |
| MTCP2 AFOSP launch ( funding with EU) | LR |  |  | x |  |  |  |  |
| MTCP2 AFOSP project meeting | LR |  |  | x |  |  |  |  |
| FFF regional ws | VS |  | x |  |  |  |  |  |
| CSA-PP regional ws | VS |  |  |  |  | x |  |  |
| Staff team building | LV |  |  |  |  |  |  | x |
| AFA execom | EP |  | x |  |  |  |  | x |
| AFA strat planning | EP |  |  |  |  |  |  | x |
| RESEARCH PAPERS |  |  |  |  |  |  |  |  |
| ILC –PPP vietnam case study | VS |  | x |  |  |  |  |  |
| CSA- PP Phil case study | VS |  |  |  | x |  |  |  |
| ILC VGGT policy papers ( 3 FOs) | EP |  | x |  |  |  |  |  |
| FFF consultations ( 8 FOs) | VS |  |  |  |  | x |  |  |
| CSA-5 years scoping on membership services (3 FOs) | VS |  |  |  |  | x |  |  |
| MANUAL |  |  |  |  |  |  |  |  |
| sustainable and inclusive enterprises | VS |  | x |  |  |  |  |  |
| ISSUE PAPERS |  |  |  |  |  |  |  |  |
| VGGT | EP |  | x |  |  |  |  |  |
| FFF | VS |  | x |  |  |  |  |  |
| CSA-PP – pakisama case | VS |  |  |  | x |  |  |  |
| youth in agri | JV |  | x |  |  |  |  |  |
| VIDEO |  |  |  |  |  |  |  |  |
| animated video manual on sustainable and inclusive enterprises | JV |  |  |  |  | x |  |  |
| Video on forest and farm facilities | JV |  |  |  |  | X |  |  |
| STORY HARVESTING |  |  |  |  |  |  |  |  |
| 2 stories per staff | all | x | x | x | x | x | x |  |
| PROJECT REPORTS ( narrative c/o assigned staff; Finance c/o MV) |  |  |  |  |  |  |  |  |
| GFAR foresight | EP |  |  | x |  |  |  |  |
| Agriterra | JV | x |  |  |  |  |  |  |
| ILC VGGT | EP |  |  | x |  |  |  |  |
| FFF | VS | x |  |  |  |  |  | Jan |
| CSA PP | VS |  |  |  |  |  | x |  |
| CSA 5 years | VS |  |  |  | x |  | x |  |
| ILC LM | JV |  |  |  |  |  |  | Jan |
| MTCP2 | LR |  |  |  |  |  |  | Jan |
| Project Proposals |  |  |  |  |  |  |  |  |
| Agriterra Aug-Dec 2015 | EP | x |  |  |  |  |  |  |
| ILC VGGT phase 2 | EP |  |  |  | x |  |  |  |
| SAARC seeds/ sustainable agri | EP |  |  |  |  |  | x |  |
| Finance Statements (FS) |  |  |  |  |  |  |  |  |
| monthly FS for AFA Execom | MV | x | x | x | x | x | x |  |
| monthly bank recon | MV | x | x | x | x | x | x |  |
| Audit 2014 | MV | x |  |  |  |  |  |  |
| Audit 2015 | MV |  |  |  |  |  |  | x |
| REPRESENTATION (staff assigned to coordinate with concerned AFA Task Force) |  |  |  |  |  |  |  |  |
| SOM AMAF | LR |  | x | x |  |  |  |  |
| GFAR | EP |  | x |  |  |  |  |  |
| WEF | EP |  |  |  |  | x |  |  |
| APAARI | EP |  |  |  |  |  | x |  |
| WRF | EP |  |  | x |  |  |  |  |
| ILC | LR |  |  |  | x |  |  |  |
| SAARC | EP |  |  |  |  |  |  |  |
| FAORAP | LR |  |  |  |  |  |  |  |
| FAO Rome/CFS | EP |  |  |  | x |  |  |  |
| Agricord | EP |  |  |  | x |  |  |  |
| GAFSP | EP |  |  |  |  |  |  |  |
| GACSA | EP |  |  |  |  |  |  |  |
| invitations from others | staff in related Task Force | x | x | x | x | x | x | x |

Legend:

LR-Lany Rebagay

VS-Vicky Serrato

LV- Lysa Villalba

EP- Esther Penunia

JV- Jun Virola

MV- Maru Ventura