CONSOLIDATED RESPONSES

to the

Questionnaire

AFA Member’s Review of Past Strategic Plan 2011-2015

In the first quarter of 2016, AFA secretariat circulated a questionnaire to Execom members . The Execom members were asked to put their assessment to the elements in the strategic plan and give a rating.

We thank API, WUA, VNFU, CTCF, NLRF for answering the questionnaire. Unfortunately, even after three follow ups, other members were not able to answer the questionnaire.

However, we have consolidated the responses of three members . Please note the rating used :

- 1 – not achieved at all

- 2 – achieved partly / fairly

- 3 – achieved satisfactorily

- 4 –achieved excellently

THE LONG-TERM PLAN

VISION: We envision Asian rural farming communities:

- Where we, small-scale women and men farmers and producers, and our families as well, are free from hunger and poverty, are happy and in good health, and live in peace and prosperity;

- Where we own or have access and control over the lands we till and other basic productive resources; nurture our farmlands through appropriate, integrated and environment-friendly agricultural practices and technologies, get fair market for our products, have control over our goods and services; and,

- Where we are self-reliant, educated and able to participate in development processes through politically strong, socially responsive, culturally sensitive and economically viable farmers’ organizations.

MISSION: We want to be a very strong and influential voice of small-scale women and men farmers in Asia. We endeavor to be a strong lobby and advocacy group for farmers’ rights and development, genuine agrarian reform and mainstreaming of sustainable agriculture in regional and national policies and programs. We also want to be a facilitator for our members’ commercial activities in trading and marketing of sustainable agricultural products. We are also a venue for solidarity and exchange of information on agriculture and farmers’ development among our members.

TAGLINE:  empowering small scale women and men farmers in Asia

PEASANT AGENDA: Our Peasant Agenda, which serves as our basis of unity, are the following:

- Promote sustainable agricultural policies and practices in family farms;

- Study and promote alternatives to economic globalization;

- Promote agriculture towards the young and build their interests towards farming;

- Promote fair and just treatment of small-scale women and men farmers in developing countries;

- Promote food sovereignty measures for small-scale women and men farmers;

- Promote farmer-to-farmer market exchanges;

- Push for ASEAN provisions on access to farm resources and rural development and protection of small-scale women and men farmers’ rights;

- Support environmentally-friendly  mitigation and adaptation measures for small-scale women and men farmers in response to climate change.

- Strengthen AFA at the national and regional levels so it becomes able to participate in international development processes.

THE MEDIUM TERM PLAN 2011-2015

1. By 2015, AFA WILL BE:

The largest, strongest, most trustworthy organization of small scale women and men farmers in Asia, working in partnership with other farmers’ organizations and other civil society organizations in pushing and implementing sustainable, environment-friendly , pro-small scale women and men farmer policies and programs at national , regional and international  levels; and while doing so, maintain the feeling of warmth and solidarity among its members and partners.

Secretariat: From 2011 to 2015, we have added 7 member organizations ( from 10 to 17 members) and added five new countries (from 8 to 13 countries), now covering Southeast, South, Northeast, and Central Asia. New donors included IFAD, SDC, EU, ILC, CSA, GAFSP, APAARI, GFAR while maintaining relations with old donor Agriterra. As gleaned from the support of EU, AFA has earned already the initial trust of big donors for financial and program management. Agriterra however, will not fund AFA anymore in 2016, because of its new priorities (focusing on local cooperatives and enterprises in several countries. AFA performed new  leadership positions  in several networks including GACSA, More and Better, GAFSP, Prolinnova, Agricord, WRF. In Asia, we are key player in the advocacy and eventual implementation of the International Year of Family Farming. We have entered a consortium with international organization La Via Campesina in implementing the MTCP2.

API : in terms of participatory research (engaging farmers in the research) there should be better effort to engage with such research agency (APAARI and GFAR), meaning involving farmers’ research and farmers as researchers (bottom-up research) based on farmers’ needs. And farmers are recognized as researchers. Furthermore, AFA as regional farmers organization should examine the possibility to have its own centers of excellence (research stations at farmers hands of selected issues).

VNFU: Yes, agree_, but AFA members should be stronger

CTCF: How to link with those regional and international supporting  organization with AFA's member organizations and how members will  benefit ?

NLRF: Continue work on small holders issues in Asia, participate from the secretariat and members organizations in most of the big events. MTCP2 given the wide exposure

SCORE Consolidated: 3.2

1.1  Performance indicators:

1.1.1   AFA has new members in Timor Leste, Laos, Myanmar, China, India, Bangladesh, Nepal, Pakistan, Bhutan.

Secretariat : Of the nine countries targetted, we have new members in three countries (Myanmar, Bangladesh, Nepal), and two non targetted countries ( Mongolia and Kyrgyztan) , thanks to our work in GAFSP. We have new members in Myanmar (AFFM), Nepal (NLRF, cTCF) , Bangladesh (KKM), Mongolia (NAMAC), Krygyzan (UWUA), Cambodia (FWN). As the year 2025 ended, Execom approved VNFU’s regular membership. In 2014, when we began to implement MTCP2, we came in better contact with farmers organizations in Laos, China, India. We are now exploring the membership of SEWA in India and Lao Farmer Network in Laos for future membership.

VNFU: Yes, agree.

CTCF: How many National FOs can get membership of AFA from each country ? Our suggestion :Maximum 3 organizations can get membership of AFA f  for 2016-2020  . After that we can change strategy.

NLRF: Good coverage and enough expertise in different field but some countries are still missing.

SCORE Consolidated  : 3.2

1.1.2. AFA members are the largest and strongest in their countries, and is sought after by national government and CSOs.

Secretariat: PAKISAMA, API, FNN, VNFU, NLRF and NAMAC are being called upon by their governments for consultation and their views are sought on some issues.

API: Improvement of the quality in terms of the consultation is needed

CTCF: How to measure largest and strongest  ?  we think we should  some indicators about them ?  and not only the largest and strongest but also professional organizations.

NLRF: Most of the member organization are well recognized and strong enough to  raise farmers voices at country level still need to improve their governance and knowledge building part

SCORE Consolidated : 3.2

1.1.3 All AFA members and Secretariat office have functional organizational structures and systems, its staff have capacities for advocacy, negotiating with governments, program and project management, financial management, networking, communication, knowledge management, sustainable agriculture.

Secretariat: AFA secretariat’s regular staff grew from 2 to 6 staff (3 for admin and finance, one each for the three programs Advocacy, Enterprise Development and KM). AFA office achieved good scores in the Agriterra financial health checklist.  Pakisama, API, FNN, FWN, AFFM, VNFU, NAMAC, NLRF, UWUA, KAFF, WAFF , Ainokai, CTCF have their own functional secretariat offices. TWADA, TDFA are assisted by volunteers from NPUST, a university. KKM secretariat is anchored by an NGO. SKP national office still not functioning, and secretariat had concerns in communication for the past three years.

API: Good achievement of ours. Congratulation! But AFA Secretariat altogether with the execom member should find time to be more focus on the open friendly discussion to facilitate SKP’s concern in order to help them back to their performance (functioning office, communication at national level). Not all of the execom members realize that concern. AFA is a big family, but if one of the member of the family has certain problem, the whole family will feel the impact. Several years ago, Thaidhrra experienced organizational problems, and as the member of DHRRA Family then Bina Desa supported them in several ways. This is a good example to help each other in solidarity spirit.

VNFU: Agree, but should be improved at regional level as well as national levels.

CTCF: ( commodity cluster formation for product , the value addition for  organic certification, Fair trade, Rain forest, Bio diversify, GAP  are needed and for marking branding, leveling, packaging , advertising support needed )

NLRF: Found all organization are  active with secretariat but need to improve their capacity.

SCORE Consolidated : 3.4

1.1.4. AFA members have concrete people-based programs (i.e. seeds selection, certification of the seeds,  support land dispute of peasants (, commodity cluster formation for production, value addition and marketing activities

Secretariat :  seeds selection (API, Pakisama, FNN, Ainokai, KKM) , certification of the seeds(API, Ainokai)  support land dispute of peasants (API, Pakisama, NLRF, AFFM) , commodity cluster formation for production, value addition and marketing activities API, PAKISAMA, FNN, SKP, VNFU TWADA, TDFA, AINOKAI, NAMAC, CTCF)

VNFU: Yes, it is good process, but it is still much improved in term of having capable staffs to do those  programs

NLRF: Programme are people based and implemented as per farmers needs

SCORE Consolidated : 3.6

1.1.5. AFA is able to finance its regional secretariat core operations and support regional programs through various but constant sources; while members are able to finance likewise their national operations. AFA secretariat has at least $150,000/year annual receipts. 80% from grants, 15% from membership and service fees, 5% from other sources.

Secretariat : AFA able to finance the regional secretariat’s core operations, and support regional programs through various constant sources. But we are dependent on donor funding almost 100%, Our membership and service fees is not even 1% of AFA operations. Most members, except SKP, are are able to finance their national operations.  Only Ainokai, KAFF, TWADA, TDFA , FNN have steady sources of funding; others  on project basis, with very short term commitments ( 1-2 years). We have to “monetize “ AFA members contributions in terms of translation and income opportunity lost when doing AFA work.

API: On one hand, AFA (the members and the secretariat) should assess how much does the proper membership fee seriously. This amount of membership fee is probably still not enough to finance our activity, but this proper amount of membership fee will somehow help enhance our sense of belonging (ownership) of AFA. On the other hand, AFA should think about business development service/BDS – and this was what we were discussing during the latest strategic planning held in Bangkok (Dec 2015).

VNFU: Agree,  and  some time contribute the cost for  administration fee for AFA activitties when t they host AFA activities

CTCF: for sustainability start to create trust fund (seed money fund). Contribution from members and donors

NLRF: Lots of work to do. We have to make guideline and will take strategic way to make members sustainable.

SCORE Consolidated: 2.4

1.1.6 The finance management systems and practices of AFA secretariat and members conform to internationally-accepted auditing and accounting principles.; its Finance Report accepted by donors

Secretariat:  Our score in the Financial health checklist of agriterra is 292 – well done. Our finance reports are accepted by donors . Executive committee receives financial reports every Execom meetings. By 2014, secretariat able to give financial reports to Execom which are better understood.

VNFU: Agree.

CTCF: It is better to develop internal audit by internal audit committee at list a end of year.

NLRF: Need to develop software and online reporting with bills and vouchers from the members to ensure best utilization of funds.

SCORE Consolidated  : 3.2

1.1.7 National governments and inter-governmental bodies have the following policies:

1.1.7.1  Very restrictive policies vs GMOs

Secretariat: Philippines has 800,000 hectares planted to GMO corn, and has been doing  field testing of BT eggplant and GMO rice. A NO2GMO coalition, in which Pakisama is part of, was able to get a temporary restraining order from Supreme Court on the commercialization of these crops. Bangladesh has BT egglplant. commercialized already. Vietnam has welcome GMO corn . ASEAN, SAARC does not have policies on GMOs.

API: AFA  at regional and national level (members) should build effective and strategic stronger coalition (among CSOs. FOs, scientists of opponents, while improved public awareness is needed regarding the GMO issues, and advocacy have to be strengthened and scientifically based. That is why AFA should have well documented alternatives of farming system (such as organic, natural, sustainable, agoecological practicesAFA members are scientist as well) that are better than GMOs matters, evident based documents, research-based advocacy then is urgent. More frequent public awareness through several media (press brief, policy brief, issue paper, leaflets, booklets, website, etc). The proponent of GMOs is well consolidated while the FOs, government, public scientists and the media are less consolidated as one integrated force.

WUA: The data above give enough evidence to continue this work

SCORE Consolidated  : 2.25

1.1.7.2 Very supportive policies on sustainable, environment-friendly agriculture and agro-based enterprises by small-scale farmers

Secretariat : Philippines has organic agriculture act. Cambodia government endorsed SRI. Nepal declared a Decade on Family Farming. SAARC, in its official summit declaration in 2014, committed to support sustainable agriculture.

API : Indonesian government has launched what so called “Go Organic” policy. In fact, it is a half-hearted policy since there have been many missed targeted practices, such as subsidies are provided to fertilizer industry to produce organic fertilizer, or to seed company to provide “certified” seeds, while farmers actually need genuine “Go Organic” policy, starting from farm level that is producing and managing its own inputs, to market level which is facilitated by the government (including access to credit, market, Participatory Guarantee System (PGS), etc.).

VNFU: Still have to work much on supportive policies on sustainable, environment-friendly agriculture and agro-based enterprises by small-scale farmers

CTCF: Focus on sustainable and organic farming policy in national and regional level .

NLRF: Made enough progress

SCORE Consolidated : 3.5

1.1.7.3 Institutionalized mechanisms for participation of FOs in agriculture-related decision-making processes.

Secretariat : FAO and AFA has just entered an MOU, and with this we have more opportunities to be invited as AFA in policy consultations of FAO.

API: congratulations!

VNFU: Still more work in this process

WUA: Not enough evidence on the progress.

NLRF: Well recognized by main organizations those are supporting to farmers organizations

SCORE Consolidated : 2.6

1.1.7.4 80% of  agriculture budget of governments are dedicated to small scale women and men farmers. United Nations has declared an International Year for Family Farming

Secretariat: United nations has declared 2014 as the International Year of Family Farming. Any info from the countries?

API : In Indonesia the IYFF has just a start in terms of socialization especially to the government and the decision-policy makers. In fact, the terms of Family Farming is not popular in Indonesia, we use the terms of farmers’ households instead. But the issue of Family Farming has actually been in the real context in our national discussion and struggle for years. With the presence of World Rural Forum office for Asia and the Pacific in Jakarta, it is our advantage to be more amplify our effort of advocacy in favour of Family Farming to several stakeholders, such as government to international agencies.

VNFU: Not sure about percentage

NLRF: Nepal government also endorsed this and made national programme  but agriculture budget not reached to small holders as expected

SCORE Consolidated: 2.5

1.1.7.5 Secured Land rights for small scale women and men farmers

Secretariat : AFA has conducted a research cum consultation on the  comparison of VGGT and existing national land laws in Cambodia, Kyrgyztan and Bangladesh. NLRF, Pakisama, API have focused programs on land rights.

NLRF: Land rights is now in AFA's priority, Got membership of ILC, Implemented VGGT, GEC and Land matrix initiative from Secretariat and members.

SCORE Consolidated : 2.8

1.1.7.6 Climate financing that support adaptation and mitigation measures for agriculture using sustainable, agro-ecological approaches

Secretariat: Green Climate Fund is operational now . We still have to study how to access these funds for our members.

API: There has been lack of popular farmers-friendly documentation on climate issue. How to bring such a “high-profile” issue on climate to down-to-earth information in order to get farmers familiar with affected issue to them is an urgent action to take. Meanwhile some farmers have been conducting good practice, experimental on adaptation and mitigation by themselves. While scientists are still far away from the ground. AFA should capable bridging this gap in order to have effective farmers-scientist partnership, hand in hand in facing this climate change. But we should be aware about the terms of CSA (climate smart agriculture), we should be precise of what is the meaning of it. At the end, there is a hope that the agricultural system is resilient to the climate where small farmers may have their sustainable livelihood with dignity, produce nutritious food, environmentally sustainable.

VNFU: can work more with donnors and funds for this agenda

SCORE Consolidated : 1.8

1.1.7.7 AFA has established its women and youth wing, with activities being implemented at regional and national levels.

Secretariat: In 2014, AFA established a youth committee and in 2015, its chairperson has been represented in AFA Execom. AFA does not yet have funds to start a process of having its women’s wing. At the membership level, API has formed its women’s committee.

API: The process of establishment of women wing at AFA should be continued, the preparation and discussion should be kept in place, while fund raising needs also to be continued

NLRF: Still to do a lot and with in AFA, the participation at the most of the programme is male dominated and little improved in last year.

SCORE Consolidated : 2

1.1.7.8. AFA has developed a concept and conducted a feasibility study for its own Enterprise at the regional level which complements and synergizes with the enterprises developed by the members.

Secretariat: AFA conducted several scoping exercises to know the enterprises of members and non members and learn from these experiences. AFA has developed a manual on sustainable and inclusive enterprises

SCORE Consolidated: 2.5

1.1.7.9. AFA is invited, consulted, and given seats and speaking slots in conferences and in mechanisms for consultation and decision–making by target institutions and agencies at national, regional and international levels.

Secretariat: At regional and international level , AFA is invited by FAO, IFAD, ASEAN, ADB, World Bank. How about at national levels ?

API: API is invited by several government agencies such as the Central Bank of Indonesia, Ministries, private institutions, and its Secretary General is now become one of a consultant of The Ministry of Village.

VNFU: VNFU is has invited by FAO, IFAD, IFOAM, ASEAN,WFO.

WUA: UWUA is invited but not as AFA member.

NLRF: Good enougH

SCORE Consolidated  : 3.2

2. OUR MAIN STRATEGIES TO ACHIEVE THIS-MEDIUM TERM PLAN:

2.1 Strategy 1: Maximize support of partners (CSOs, government and intergovernmental bodies, other FOs) in the promotion of our agenda by increasing networking activities and forging concrete partnership projects with them.

Secretariat: AFA has gained many partners and supporters among CSOs, government, and inter-government bodies, as well as other farmer organizations at the regional and international levels. It is active in different regional and international network and coalitions. These networks and coalitions became venues for AFA’s advocacy activities in the past and they will continue to do so.  Our membership with ILC, and active participation in GAFSP, GFAR, APAARI  FAO and IFAD have resulted in concrete project/program partnerships. With regards partnership with CSOs, AFA is key player in the CSO network dealing with FAO , CFS, and ASEAN concerns. In 2014, AFA started engagement with CSOs working with Peoples’ SAARC.

API : AFA should maximize its position and roles in each partnership in favour of its members.

CTCF: Explore other organizations like as ILO,  NEDAC( Network for the Development of Agricultural Cooperatives in Asia and the Pacific )

NLRF: Happening this perfectly

SCORE Consolidated: 3.4

2.2. Strategy 2: Make AFA an effective Knowledge and Learning Hub: Capturing and Sharing Knowledge and Lessons Learned by FOs

AFA will utilize knowledge management strategies and practices in order to maximize its efforts by ensuring that knowledge is captured and shared and learning occurs within the organization. AFA will strengthen its knowledge and learning hub; it will have online and offline activities, operating at national and regional levels to ensure a dynamic sharing of knowledge and inspire faster learning curves. AFA will capture and share knowledge and lessons learned through the (a) establishment and maintenance of a website that will serve as a venue for online interaction; (b) creation of knowledge products such as manuals, video demonstrations, best practice catalogues, comics, programming guides for radio or TV programs, all of  which should include acknowledgement of the innovators, adapters as well as the funding support; (c) regional experience sharing, farmers’ exchange visits, study tours, cliniquing sessions, member-to-member assistance, knowledge fairs, farmer-to-farmer extension, search for best practice through competitions to promote the knowledge products, serving as the offline interaction for AFA members; (d) monitoring and documenting results of technology adopters (farmers) and various organizational systems and processes to cull out learning and new innovations they introduced.

Secretariat: AFA has website, facebook, twitter accounts, MTCP2/AFOSP blogs. WE have conducted member-to-member cooperation under the Agriterra project, as well as some learning exchanges under MTCP2/AFOSP. Within AFA, we need to discuss better, more effective sharing and communication systems so that each one gets to know what the other members are doing.

API: Not all of our members are well-literate with such technology of electronic multimedia/social media, while most of us are living in remote areas, where access to the internet connection is quite poor. Tangible printed handy material is still needed. We can copy the material in low price edition, but should be presented in a popular well understood, farmers-friendly ones.

NLRF: The efforts doing from secretariat is good but there is scope to make this most popular and two way.

SCORE Consolidated: 3

2.3 Strategy 3: Diversify sources for financing and technical support, through internal and external resource generation and Effective Secretariat Management

AFA will tap new donors and AFA members will liaise with these new donors (e.g. ASEAN Foundation c/o API, ADB c/o Pakisama, FAORAP c/o SKP, WOCAN c/o SKP, Greater Mekong Commission c/o FNN, IFAD–Asia c/o Secretariat), exploring possibilities for partnership and ensuring smooth relationships. To continuously generate ideas which can facilitate development of concept notes and proposals, virtual secretariat meetings will be held at least once a month. Knowledge generated from knowledge sharing activities will be used. To increase internal resource generation, AFA will explore a regional business enterprise, which complements the marketing initiatives of its members, and conduct a serious feasibility study on the options at hand. AFA will also explore other fund-raising activities (e.g. adopt-a-farming-community project, adopt-a-PO-project).

Secretariat: We have diversified donor sources, but AFA’s funds still from external donors. There were suggestions to increase membership fees and annual dues, or for member organizations in “richer” countries to contribute more to AFA.

API : Absolutely agree with the proper membership fee. See the previous assessment related to the membership fee.

VNFU: it is depends cases.

CTCF: for sustainability start to create trust fund (seed money fund). Contribution from members and donors

NLRF: need to develop sustainability and internal source generation plan in each country level.

SCORE Consolidated: 2.6

KEY PROGRAMS

Advocacy. Conducting activities related to policy information, policy analysis and campaigns, as well as networking with other organizations, and lobbying and dialogues with decision-makers and influential persons and organizations.

Secretariat: We have carried our various consultations at AFA level on VGGT, farmers in forested landscapes, youth in agriculture, family farming. We have represented the voice of asian farmers in various regional and international fora.

API: Present more case studies of related issues from members (good practices, on ground/grass-root innovations), so we provide our evident-based findings, success stories, learning experience, and voice them out to various regional and international for a better

CTCF: Develop the Capacity and skill of FOs leaders for Advocacy

NLRF: AFA have been organized capacity building events regularly.

SCORE Consolidated : 3.2

Knowledge Management and Sharing. Developing the knowledge and skills of our leaders and members through capturing the knowledge generated from on-ground experiences of members, and then sharing them through online and offline activities.

Secretariat :  All issue papers produced have been translated to languages of interested members. Topics included land rights, youth in agriculture, sustainable and inclusive enterprises, members’ experiences and initiatives.

API: More picture information, comics, while the format of issue paper is too serious to farmers. Is there another creative way to produce such information? It should be presented per country, deeper story

NLRF: This is one of the innovative efforts to exchange farmers knowledge in Asia and this is good connecter

SCORE Consolidated: 3.2

Enterprise Development. Technical and managerial support to member’s initiatives in sustainable agriculture production and marketing, and enterprise development, as well as developing an enterprise at the regional level.

Secretariat : We have conducted consultations on organic agriculture supported by Agriterra, sustainable and inclusive marketing arrangements and FO capacity to deliver economic services to members and engage govt on public procurement supported by CSA. In 2015 during the strategic planning exercise, members identified AFA as a business service provider .

API: we will see the progress of the regional BDS. Seems to have more focused discussion on this issue.

VNFU: Agree , but it is still should be trained for AFA members.

CTCF: Motivate individual households  farmers in cooperative and support them in business motive activities.

NLRF: Need to be increased.

SCORE Consolidated: 2.6

Governance. Ensuring that organizational systems and processes for decision making and management are maintained and upgraded so that we can be transparent, democratic, effective, efficient  and able to sustain our core operations.

Secretariat: We have regularly held Execom and GA, welcomed and made inputs to the aGriterra evaluation, formed task forces to increase membership involvement in AFA affairs.

API: we will wait for the report progress of the task forces

CTCF: AFA can develop some  own evaluation tools for assessment in good  governance  and services

NLRF: Still there is area of improvements

SCORE Consolidated: 2.8